## Sheet1
Part number	Part name	Model status	Number required for emc	notes
	Z-upper right	Ready to print	1	passed torque 8 in-lbs, passed pullout (6x M3's) used to mount non-axially loaded part that is mounted to a plate
	Z-upper Left	Ready to print	1	passed torque 8 in-lbs, passed pullout (6x M3's) used to mount non-axially loaded part that is mounted to a plate
	Z-lower left	Ready to print	2
	Z-lower right	Ready to print	2
	X-end motor	Ready to print	2
	X-end idler	Ready to print	2
	strain relief mount	Ready to print	0
	strain relief mount lower	Ready to print	0
	Y-idler	Ready to print	2
	y rod mount	Ready to print	2
	double bearing holder	In testing	4
	belt mount	Ready to print	0	6 in-lbs closes clamp and does not split insert side of mount; 8 in-lbs of torque will split insert side of clamp; mount inserts passed torque 8 in-lbs, passed pullout (3x M3's) used to secure mount plate
	bed corner	Ready to print	8
	wiper mount	Ready to print	2
	handle	Ready to print	1	Chamfer for inserts to be included, excess plastic bloom; increase insert hole depth- Soldering iron tip extends beyond insert by 1.5mm. Total hole depth to be near 5.4mm
	X-carriage cap	Ready to print	2
	upper x bearing holder	Ready to print	2
	X-carriage	Ready to print	2
	extruder mount	Ready to print	0	Fan mount M3 holes crack at 8 in-lbs torque applied, pull out force is acceptable, front M3 passed 8 in-lbs torque and pull out
	heatsink fan mount	Same as Olive	2	pull from current olive
	extruder body	Same as foxglove	2	use same gcode as foxglove
	Beefy extruder idler	NEW!!	0	We are going to roll with the extruder idler and latch from Opah, files have been updated
	extruder washer	Ready to print	0
	Beefy idler latch	NEW!!	2	We are going to roll with the extruder idler and latch from Opah, files have been updated
	small herringbone	Same as foxglove	0
	large herringbone	Same as foxglove	0
	Spool arm	Ready to print	0
	spool arm support	Ready to print	2
	spool arm bracket	Ready to print	0
	bed clip	Ready to print	0	test parts do not fit bed connectors, parts (2) cracked
	upper bearing	Ready to print	2
	extruder fan mount	Ready to print	0